Introduction to Software Engineering

Weekly Status Report

The student team is required to complete the Weekly Status Report documentation for the assigned course project, following the attached template.

Software Engineering Department

Faculty of Information and Technology

University of Science

Table of Contents

Objectives	1

1 Submission	2

2 Report Information	3

2.1 Task Status	3

2.2 Plan for Next Week	4

2.3 Issues and Risks	4

2.4 Meeting Minutes	5

2.5 Metrics	6

Weekly Status Report

# Objectives

This document focus on the following topics:

- Reporting weekly progress against the project plan

- Recording issues and risks

- Recording the weekly status meeting

# Submission

- One report per week, from week 2 to week 10 (9 reports). The team lead (or backup) is responsible.

- The team chooses its own weekly deadline (e.g., the day after the status meeting) and states it in PA1.

- Commit the report to the repository: /docs/management/weekly/W<week>-status.docx (or .md), e.g., W03-status.docx. Do not overwrite or rewrite earlier reports; the commit history is the evidence of timeliness.

- Reports are not submitted on Moodle. They are graded at the end of the course as part of the Teamwork & tool usage component (working process).

# Report Information

| Item | Value |
| --- | --- |
| Team | T04 |
| Week | 4 |
| Date of meeting | 23/10/2026 |
| Current phase / PA | PA2 |
| Prepared by | Trần Anh Khoa |
| Overall status | Green (on track) |

## Task Status

| WBS / task | Owner | Planned finish | Status | % done | Notes |
| --- | --- | --- | --- | --- | --- |
| W04-01 Prepare the PA2 introduction, problem statement, glossary, and stakeholder descriptions based on PA1. | Thúy | 22/10/2026 | Done | 100% |  |
| W04-02 Draft functional and non-functional requirements for the five Must-have features, including basic business rules and acceptance criteria. | Thúy | 26/10/2026 | Done | 100% |  |
| W04-03 Identify main actors and use cases, prepare the Use Case Diagram, and draft key use case descriptions. | Thúy | 26/10/2026 | Done | 100% |  |
| W04-04 Prepare Figma wireframes for the main screens, including login, forum, and fundraising campaigns. | Bảo | 26/10/2026 | Done | 100% |  |
| W04-05 Review initial design goals and prepare the basic system architecture based on PA1 and the developing PA2 requirements. | Bảo, Phước | 26/10/2026 | Done | 100% |  |
| W04-06 Prepare the frontend, backend, and database development environments for the upcoming implementation phase. | Phước | 26/10/2026 | Done | 100% |  |
| W04-07 Review drafted requirements, identify missing information, and start the Requirements Traceability Matrix (RTM). | Khoa, Thúy | 26/10/2026 | Done | 100% |  |
| W04-08 Update GitHub Projects, review weekly progress, and prepare the W04 Weekly Status Report. | Khoa | 27/10/2026 | Done | 100% |  |

## Plan for Next Week

| WBS / task | Owner | Planned finish |
| --- | --- | --- |
| W05-01 – 2.6.1 Prepare the Requirements Traceability Matrix (RTM) | Thúy, Khoa | 01/11/2026 |
| W05-02 – 2.6.2 Conduct the requirements review and record resolutions | Thúy | 02/11/2026 |
| W05-03 – 2.6.3 Confirm the requirements baseline | Thúy | 02/11/2026 |

## Issues and Risks

| ID | Description | Impact | Action | Owner | Due |
| --- | --- | --- | --- | --- | --- |
| R04-01 | The Requirements Traceability Matrix (RTM) has not been completed. | Some functional requirements may not be mapped to the corresponding screens or design components. | Create the RTM and verify the mapping between requirements, use cases, and Figma screens. | Thúy, Khoa | 27/10 |
| R04-02 | The interactive prototype may have incomplete user flows or missing screen transitions. | Users may be unable to complete key workflows, and the prototype may not fully demonstrate the system requirements. | Connect the Figma screens and test the main flows for authentication, forum, campaign management, and donation. | Bảo | 02/11 |
| R04-03 | Architectural and object-oriented design tasks may require more time than planned. | Design diagrams and documentation may be delayed, affecting subsequent development activities. | Prioritize the architecture diagrams and core domain/class models; divide tasks among team members where possible. | All members | 02/11 |
| R04-04 | Requirements or design decisions may remain unclear during the review. | Inconsistent assumptions may lead to rework in diagrams, prototypes, or implementation. | Conduct a team review, document unresolved questions and decisions, and confirm the requirements baseline. | Thúy | 02/11 |

## Meeting Minutes

| Member | Present | Done since last meeting | Next | Blockers |
| --- | --- | --- | --- | --- |
| Trần Anh Khoa | Present | Reviewed the Figma screen design progress across the team, checked consistency with project requirements, and provided feedback on task completion and UI consistency. | Review the integrated Figma prototype, provide feedback on UI/UX consistency, and monitor the completion of Week 5 tasks. | None |
| Hồng Gia Bảo | Present | Reviewed UI/UX design requirements and contributed to the Figma screen design plan. Completed the assigned screens for campaign creation and campaign approval/moderation (FL-03 and FL-04). | Connect the campaign-related screens into interactive flows and contribute to the system architecture and design diagrams. | None |
| Nguyễn Trần Phương Thúy | Present | Coordinated task allocation and reviewed the progress of Figma screen design. Helped align the screen design tasks with the project schedule and team responsibilities. | Review the integrated Figma prototype, track Week 5 tasks, and coordinate requirements traceability and design activities. | None |
| Lê Nho Duy Phước | Present | Reviewed the technical and UI requirements and completed the assigned Figma screens for community forum and forum moderation (FL-02 and FL-06), as well as donation and progress tracking (FL-05). Contributed to identifying shared UI components. | Help finalize shared UI components, review the donation and forum user flows, and contribute to the domain model and class diagram. | None |

## Metrics

| Metric | This week | Total |
| --- | --- | --- |
| Tasks completed | 8 | 8 |
| Commits | 2 | 17 |
| Pull requests merged / reviewed | 1 merged | 3 merged |
| Open defects (PA5) |  |  |